| Goals / Objectives / Activities | Start Date | Estimated Completion Date | Budget Amount (If activities have a cost) | Who is responsible? Who is Participating? | Data Collection Sources to Measure Success | Evaluation Plan |
| --- | --- | --- | --- | --- | --- | --- |
| Project description: This project is funded by a State Longitudinal Data System (SLDS) grant funded by the US Department of Education, National Center for Education Statistics with supplemental funding made available through the American Recovery and Reinvestment Act (ARRA) that is also supporting the creation, work and goals of the Wisconsin Governor’s Early Childhood Advisory Council (ECAC). The third stage of the Wisconsin SLDS project involves expansion of the LDS to include information about children ages birth to five. Outcomes identified in the grant for early childhood first address the need to identify the multitude of programs and services within the State that serve these children. After programs and services are identified, analysis will be completed to determine what data is currently collected, available, and transportable. This analysis will help determine the feasibility of linking data from the different programs and services together, and to the existing LDS, and identify existing data gaps. |
| Goal 1 Create an inventory of early childhood programs and services, and the data currently collected by these programs and services (including individual-, provider-, and program-level data). Particular emphasis should be placed on those programs that collect data at the individual child or workforce level. This document should also include information about the accessibility, quality, and transferability of collected data, as well as identify existing data gaps. |
| Objective 1: Analysis of the current early childhood data environment |
| Activity 1.1 Contact New York Early Care & Learning Council (ECLC) and NYS Council on Children and Families (CCF) to obtain a copy of survey sent to agencies providing services to young children to identify the elements their data systems collect and accessibility of those elements. | 8/15/2011 | 9/01/2011 | NA | Carol Noddings Eichinger | Copy of elements and questions available for Project Team to review. | Critical analysis of match between ECDC essential elements, Wisconsin priorities, and recommended edits. |
| Activity 1.2 Complete data component for criterion E2 to the Race to the Top Application. | 09/01/2011 | 10/10/2011 Complete | NA | DCF, Hillary Shager and Project Team | Completed application for approval | Application submitted |
| Activity 1.3 Field and analyze the survey, making modifications to match Wisconsin’s key priorities for data. Determine whether to deliver in survey format or face-to-face interviews. | 10/01/2011 | 11/01/2011 | NA | Carol Noddings Eichinger, June Fox, Project Team | Adapted survey addressing Wisconsin’s unique priorities. Or, interview questions addressing Wisconsin’s unique priorities. | Survey ready to launce on Vovici or interview questions ready |
| Activity 1.4 Review Wisconsin Early Childhood Assessment System Report submitted by Katherine Magnuuson from the University of Wisconsin-Madison to ECAC in 2010. | 8/01/2011 | 11/01/2011 | NA | Carol Noddings Eichinger and June Fox | Data Sources from analysis integrated into development of survey. | Familiarity with system analysis and gaps as reflected in final survey |
| Activity 1.5: Design survey or interview, including exploration of 10 core data elements defined by Early Childhood Data Collaborative (ECDC). Explore DPI Vovici survey that offers live, electronic data on demand. | 11/01/2011 | 12/31/2011 | NA | June Fox, Carol Noddings Eichinger, Project Team | Completed Survey | Survey displays intersection of ECDC components and Wisconsin data sources. |
| Activity 1.6: Determine key agencies to contact initially. Determine second stage agencies to contact. | 11/15/2011 | 12/31/2011 | NA | Project Team | List of first stage and second stage agencies. | List vetted with ECAC |
| Activity 1.7 Set-up preliminary meetings with DHS, DPI, and DCF to identify key data personnel and key data sets from programs serving young children. | 10/25/2011 | 12/31/2011 | NA | June Fox, Rod Packard | Completed chart of key program, system, and data sets for each department | Chart shared with Project Team |
| Activity 1:8 Identify key personnel to facilitate completion of survey within that agency or to answer interview questions. | 11/30/2011 | 12/31/2011 | NA | Project Team | List of key personnel. | Key personnel contacted for Data Roundhouse and for completion of survey. |
| Activity 1:9 Determine who issues invitation/request to complete survey (Contacts from Activity 1.7 and/or ECAC members) Or who makes initial contact to conduct interview. | 11/30/2011` | 12.31.2911 | NA | Project Team | Delegation of initial contact/invitation from Project Team members. | Key personnel contacted for Data Roundtable and for completion of survey. |
| Activity 1.10 Launch survey and summarize results from survey and/or conduct interviews and summarize results from interviews. | 12/31/2011 | 3/15/2012 | ?? | June Fox and Carol Noddings Eichinger | Survey completed or interviews completed | Results shared with Project Team, indicating data elements currently collected by each program. |
| Objective 2: Identify alternative strategies for assigning a unique identifier to children in Wisconsin consistent with ECDC guidance |  |
| Activity 2.1 Review of Vovici Survey/interview results to clarify which programs are using a unique child ID. | 12/31/2011 | 1/31/2012 | NA | Carol Noddings Eichinger & June Fox | Listing of programs/agencies utilizing unique child ID. | Completed list presented to Project Team. |
| Activity 2.2: Access ECDC guidance, and guidance from the National Center for Education Statistics EC Support Team. | 9/01/2011 | 1/31/2012 | NA | Carol Noddings Eichinger & June Fox | Summary document of key guidance. | Guidance reviewed with Project Team. |
| Activity 2.3: Research other precedents from states further along in process | 9/01/2011 | 1/31/2012 | NA | Carol Noddings Eichinger & June Fox | Summary document of key precedents from other states. | Summary reviewed with Project Team. |
| Activity 2.4: Meet with Maria Cancian & Jennifer Noyes on the Wisconsin Administrative Data Core project. (Institute for Research on Poverty-UW-Madison) | 09/01/2011 | 11/15/2011 | NA | Hillary Shager, Rod Packard, Jill Haglund, Carol Noddings Eichinger, June Fox | Minutes from meeting outlining key recommendations. | Key understandings from Data Core Project considered for EC LDS Project. |
| Objective 3: Identify alternative strategies for assigning a unique identifier to program sites within Wisconsin consistent with ECDC guidance |  |
| Activity 3.1: Review of Vovici Survey/interview results to clarify which programs are using a unique ID. | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Listing of programs/agencies utilizing unique program ID | Completed list presented to Project Team. |
| Activity 3.2: Access ECDC guidance , and guidance from the National Center for Education Statistics EC Support Team. | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Summary document of key guidance | Guidance reviewed with Project Team |
| Activity 3:3 Research other precedents from states further along in process | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Summary document of key precedents from other states. | Summary reviewed with Project Team |
| Activity 3.4: Review of Vovici Survey/interview results to clarify which programs link program ID and workforce ID. | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Summary document of programs prepared. | Summary reviewed with Project Team |
| Objective 4: Identify alternative strategies for assigning a unique identifier to the early childhood workforce within Wisconsin consistent with ECDC guidance |
| Activity 4.1 Review of Vovici Survey/interview results to clarify which programs are using a workforce ID. | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Listing of programs/agencies utilizing unique workforce ID | Completed list presented to Project Team. |
| Activity 4.2: Access ECDC guidance , and guidance from the National Center for Education Statistics EC Support Team. | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Summary document of key guidance | Guidance reviewed with Project Team |
| Activity 4.3 Research other precedents from states further along in process | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Summary document of key precedents from other states. | Summary reviewed with Project Team |
| Activity 4.4 Review of Vovici Survey/interview results to clarify which programs link workforce ID with education and professional development information. | 12/31/2011 | 1/31//2011 | NA | Carol Noddings Eichinger & June Fox | Summary document of programs prepared. | Summary reviewed with Project Team |
| Goal 2 Establish data sharing methodologies |
| Objective 1: Build consensus around common data elements and common data standards |
| Activity 1.1 a. Initial framing of Wisconsin questions by EC LDS Project Team July 28, modifying the national Early Childhood Data Collaborative six policy statements. b. Pose question to WECCP Early Childhood Regions at August 11, 2011 Video-Conference for reactions. | 8/01/2011 | 11/15/2011 | NA | Project Team and Carol Noddings Eichinger | Powerpoint presentation for 8/11/2011 Videoconference | Address feedback from audience on two key data questions posed at videoconference. |
| Activity 1.2 Work with IRP and other LDS department data experts around details. | 10/01/2011 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Data Dictionary of common data elements across systems. | Incorporation of key data elements identified by Data Quality Campaign |
| Activity 1.3: Identify and address existing data gaps | 12/31/2011 | 3/15/2012 | NA | Project Team, June Fox | Recommendations for considering “filling the gaps” | Recommendations presented by Project Team to ECAC |
| Goal 3 Begin data sharing process |
| Objective 1: Identify opportunities to exchange data in order to meet the long term objectives of the ECDC and work to establish a sequence of activities that best meet the needs of Wisconsin |
| Activity 1.1 Brief introduction at Collaborating Partners Video-Conference August 11, 2011, to WECCP Early Childhood Regions | 8/01/2011 | 11/15/2011 | NA | Carol Noddings Eichinger, Dave Edie, Linda Leonhart | Powerpoint from Videoconference | Review of feedback from two key data questions from videoconference |
| Acitivty 1.2 Develop a clear and well-articulated purpose for the EC Data System. | 11/01/2011 | 12/31/2011 | NA | Project Team | Purpose articulated for public messaging. | Message utilized on documents and website. |
| Activity 1.3 Set up “internal” short briefings with Wisconsin main departments (DCF, DWD, DHS and DPI) with administrative and key data personnel, “hosted” by EC LDS Project Team members. Identify key department personnel to attend a half day “Data Roundtable”. | 11/01/2011 | 12/31/2011 | Costs? | Project Team, Carol Noddings Eichinger, June Fox | Format created for internal meetings. | Meetings scheduled and feedback evaluated. |
| Activity 1.4 Identify other key stakeholders and clarify the reason for their inclusion at the Data Roundtable. | 11/01/2011 | 12/31/2011 | NA | Project Team | List of invitees for Data Roundtable | Invitations issued. |
| Activity 1.5: Set up a “Data Roundtable” to provide a major over-view of data plan/intentions and workshop for exploring possibilities in a half day meeting with key stakeholders, similar to the process used in Oklahoma | 11/01/2011 | 12/31/2011 | Costs for meal/space? | Project Team, Carol Noddings Eichinger, June Fox | Data Roundhouse scheduled and completed. | Evaluation of audience satisfaction with event |
| Activity 1.6: Contact potential facilitators, including Elliot Regenstein who facilitated the Oklahoma Data Roundtable, and has worked with WI ECAC before. elliot.regenstein@educationcounsel.com | 11/01/2011 | 12/31/2011 | Collect proposed costs for approval from Project Team. | Project Team, Carol Noddings Eichinger, June Fox, Linda Leonhart | List of potential facilitators and costs generated for Project Team Review. | Facilitator chosen and successful completion of event. |
| Activity 1.7: Contact Andy Feldman from BadgerStats to explore public data sharing strategies. | 09/12/2011 | 11/15/2011 | NA | Carol Noddings Eichinger and Dennis Winters | BadgerStat website http://badgerstat.org/ review | Share website details with Project Team. |
| Activity 1.8: Meet with personnel Luanne Platt and Jare Wallden from the Registry to explore current data sharing | 10/04/2011 | 11/15/2011 | NA | Carol Noddings Eichinger,June Fox | Summary of current data sharing and recommendations | Presented to Project Team |
| Activity 1.9 Meet with personnel in Milwaukee involved in KIDS integrated data system | 09/15/2011 | 11/15/2011 | NA | Hillary Shager, Rod Packard, Jill Haglund, Carol Noddings Eichinger, June Fox | Minutes of recommendations from meeting. | Recommendations presented to Project Team. |
| Activity 1.10: Meet with personnel involved in the Racine School Readiness Coalition Longitudinal Data Monitoring System (Carole M. Johnson, Director, The Johnson Foundation at Wingspread) and from the Brown County Community Data Base Project. | 09/15/2011 | 11/15/2011 | NA | Hillary Shager, Rod Packard, Jill Haglund, Carol Noddings Eichinger, June Fox | Minutes of recommendations from meeting. | Recommendations presented to Project Team. |
| Activity 1.11 Participate in the Early Childhood Work Group sponsored by NCES in Washington DC, November 14, 2011. Implement the planning tool from this work group as a State Pilot. | 10/25/2011 | 3/15/2012 | NA | Carol Noddings Eichinger, June Fox, Hillary Shager | Participation in the Work Group. | Implementation of the planning tool created by the Work Group as a guidance resource. |
| Activity 1.12 Participate in the Early Childhood sections of the SLDS P-20W Best Practice Conference in Washington DC November 14-16, 2011 | 11/14/2011 | 11/16/2011 | Costs to the LDS grant as required | Rod Packard, Carol Noddings Eichinger, Hillary Shager | Participation at the conference | Materials and guidance from conference shared with Project Team |
| Objective 2: Determine how and when identified data elements can be added to the EC LDS, collaboratively with key date personnel. |
| Activity 2.1: Review data elements from Common Education Data Standards document. Synchronize with key data variables from 10 components | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Recommendations from review. | Recommendations presented to Project Team. |
| Activity 2 .2: Identify short term (low-cost, high return) opportunities for data linkages. Include stakeholders from the “Data Roundtable”. | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Recommendations identified. | Recommendations presented to Project Team. |
| Activity 2.3: Identify long term data sharing architecture and strategies. Include stakeholders from the “Data Roundtable”. | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Recommendations identified. | Recommendations presented to Project Team. |
| Goal 4 Develop strategies for data governance and long term system usage |
| Objective 1: Identify strategies for data governance and usage |
| Activity 1.1 Identify best practices from other key states; Pennsylvania, New York, Maryland, Oklahoma. | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard, Carol Noddings Eichinger | Recommendations identified. | Recommendations presented to Project Team. |
| Activity 1.2 Review the practices of Wisconsin current LDS in the areas of data governance and usage strategies | 10/19/2011 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard, Carol Noddings Eichinger | Current practices summarized | Current practices presented to Project Team and noted in the EC LDS web page. |
| Activity 1.3 Review the practices of Wisconsin current DHS and DCF systems in the areas of data governance and usage strategies | 10/19/2011 | 3/15/2012 | NA | June Fox, DCF and DHS technical personnel, | Current practices summarized | Current practices presented to Project Team and noted in the EC LDS web page. |
| Activity 1.4 Access guidance from the National Center for Education Statistics EC Support Team. | 10/25/2011 | 3/15/2010 | NA | June Fox and Carol Noddings Eichinger | Document TA provided by NCES | Guidance presented to Project Team |
| Activity 1.5 Create transparency through establishment of a EC LDS Web page to post ongoing activities and practices. | 11/15/2011 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard, Carol Noddings Eichinger | Website created. | Stakeholder feedback assessed. |
| Activity 1.6 Create and execute communication plan. | 11/15/2011 | 3/15/2012 | NA | June Fox, Rod Packard, Carol Noddings Eichinger | Completed Communication Plan | Project Team Review |
| Objective 2: Identify strategies for data quality assurance |
| Activity 2.1. Research other state’s plans to ensure that data is first collected/reported/used properly within the state education agency(intra-agency data governance). | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Recommendations identified. | Recommendations presented to Project Team. |
| Activity 2.2 Research other state’s plans to ensure data is linked and exchanged properly with other state agencies (inter-agency data governance). | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Recommendations identified. | Recommendations presented to Project Team. |
| Activity 2.3 Review the practices of DPI current LDS in the area of data quality assurance | 10/19/2011 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard, Carol Noddings Eichinger | Current practices summarized | Current practices presented to Project Team and noted in the EC LDS web page. |
| Activity 2.4 Review the practices of current DHS and DCF systems in the area of data quality assurance | 10/19/2011 | 3/15/2012 | NA | June Fox, DCF and DHS technical personnel, | Current practices summarized | Current practices presented to Project Team and noted in the EC LDS web page. |
| Activity 2.5 Develop list of recommendations about governance policies, defining MOU’s, common standards, support from state-level policymakers, and passing legislation. | 1/01/2012 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard | Recommendations identified. | Recommendations presented to Project Team. |
| Activity 2.6 Access guidance from the National Center for Education Statistics EC Support Team. | 10/25/2011 | 3/15/2010 | NA | June Fox and Carol Noddings Eichinger | Document TA provided by NCES | Guidance presented to Project Team |
| Objective 3: Identify strategies for privacy protections and security practices and policies |
| Activity 3.1 Review the practices of DPI current LDS in the areas of privacy protections and security practices and policies. | 10/19/2011 | 3/15/2012 | NA | June Fox, LDS personnel, Rod Packard, Carol Noddings Eichinger | Current practices summarized | Current practices presented to Project Team and noted in the EC LDS web page. |
| Activity 3.2 Review the practices of current DHS and DCF systems in the areas of privacy protections and security practices and policies. | 10/19/2011 | 3/15/2012 | NA | June Fox, DCF and DHS technical personnel, | Current practices summarized | Current practices presented to Project Team and noted in the EC LDS web page. |
| Activity 3.3 Further clarify other privacy measures and law impacting agencies/departments (HIPAA, FERPA, Headstart, etc.) |  |  |  | June Fox, LDS personnel, Rod Packard | Recommendations identified. | Recommendations presented to Project Team. |
| Activity 3.4 Access guidance from the National Center for Education Statistics EC Support Team. | 10/25/2011 | 3/15/2010 | NA | June Fox and Carol Noddings Eichinger | Document TA provided by NCES | Guidance presented to Project Team |
| Objective 4: Identify strategies for engaging state and local stakeholders in system building and sustainability efforts (ECAC, policy makers, researchers, service providers and parents) |
| Activity 4.1. Identify key stakeholder groups and individuals with those groups. | 11/01/2011 | 3/15/2012 | NA | Carol Noddings Eichinger, June Fox, Project Team and ECAC | Stakeholders identified | List complete |
| Activity 4.2 Identify key funders. | 11/01/2011 | 3/15/2012 | NA | Carol Noddings Eichinger, June Fox, Project Team and ECAC | Key funders identified | List complete |
| Activity 4.3 Write strategic document with stakeholders and funders listed, make a case for benefits each stakeholder would receive from the system, if system is developed and implemented | 11/01/2011 | 3/15/2012 | NA | Carol Noddings Eichinger, June Fox, Project Team and ECAC | Document completed | Document presented to Project Team and ECAC |