## Sheet1
EC LDS PROJECTED WORK PLAN: FEASIBILITY STUDY / DEVELOPE INITIAL IMPLEMENTATION PLAN
2012 | [8 empty] | 2013
April | May | June | July | August | September | October | November | December | January | February
Capacity Recommendations: Underlying Questions/Data Survey Results/Select Low-Hanging Fruit |  |  | Data Governance - Recommendations (structure, policy guide and universal MOU draft development) |  |  |  |  | Suggest Potential System Architecture, Stakeholder Engagement and EC LDS Sustainability Recommendations | Finalize Initial Implementation Work Plan - Really is Draft Workplan for RTTT -ELC
Complete Survey Work | Unique Identifiers Recommendations |  |  |  | Race To The Top - Early Learning Challenge (RTTT ELC) Grant Application - Round 2