## Sheet1
What | Cohort 1 Schools That Opt to End in Spring 2018 (original end date) | Cohort 1 Schools that Opt to Extend Their Project | Cohort 2 Schools | How many times? | Who | How | How long will it take? | Why
TSS Fidelity Tool | Every Spring during the project, and one last time at the end of the project. (Last submission due Dec. 2018) | Spring 2018, Spring 2019, Fall 2019 (by Dec) | Every Spring during the project, and one last time at the end of the project. (Last submission due Dec. 2019) | 4 | Your TSS team. | You choose either online or paper. | 15-45 minutes, depending on your team | The tool itself helps you and the evaluators see how far along you are in implementing TSS, and can be used to help guide implementation.
Staff attendance and retention data | By June 30 every year in project, and again at project end. | Last submission due Summer 2019 | By June 30 every year in project, and again at project end (Summer 2019). | 4 | Principal or administrator | Fill out a form provided by DPI. | Depends on school records/IT system | In theory, TSS should increase morale, resulting in less absenteeism and better staff retention.
School climate surveys | Spring 2016 and Spring 2018 | Spring 2019 (not 2018) | Spring 2017 and Spring 2019 | 2 | Students (grades 5, 6, 8, 10, 12); Parents; Faculty/staff | Online | Approx. 30 minutes | Very comprehensive data that will help you see strengths and gaps both for the MH initiative and for TSS
Conversations with school personnel, students | Beginning Spring 2017 | N/A | Beginning Spring 2018 | 2 | TSS Team, a handful of additional staff and students/parents | In-person focus groups or interviews with DPI evaluators | Approx. 45 minutes per interview/focus group | To get a more in-depth sense from schools of what's working well, what's difficult, and how TSS is changing their schools
Teacher questionnaire (ARTIC) | Spring 2016 and Spring 2018. | Spring 2019 (not 2018) | Spring 2017 and Spring 2019 | 2 | All teachers | TBD | 2-3 minutes | To determine teacher attitudes towards TSS practices and perspective, both near the beginning and at project end.
Submit TSS-enhanced policies and procedures (if available) | Project End (Due by Dec. 2018) | Due by Dec. 2019 | Project End (Due by Dec. 2019) | 1 | Administrator | Email attachments to DPI evaluators | Time it takes to send email attachments | For schools to be able to showcase any changes they may have made as a result of TSS, and as a resource for other schools.